Braywood 3 year PE Action Plan 2019-2022

| Priority 1: To ensure sustainable high quality teaching and learning |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Monitoring | RAG Evaluation and Milestones July 2020 July 2021 July 2022 |  |  | Success Criteria |
| Commit to membership of WSP and their support to develop sustainable knowledge, skills and pedagogy especially for teachers new/less experienced with their year group System of Mentoring & coaching in place Effective subject Leadership Ensure PE equipment appropriate, in good condition & accessible | Subject Leader Teachers Teaching Assistants | Head teacher PE Subject Leader PE Governor | Teachers observe and support WSP coaches to deliver lessons (ongoing) Monitor (ongoing) PE lead/HT to identify CPD needs throughout staff & book appropriate WSP training &/or internal coaching /mentoring Continued WSP CPD for 2 TA PE specialists SL&/or TA PE specialist to attend WSP network meetings and share best practice and training with all (ongoing) WSP/PE lead review of PE and physical activity at Braywood System in place for monitoring of PE & lunchtime equipment stores for availability, access to & condition of equipment PE subject leader to observe each teacher at least once per year and less experienced twice PE Governor to review PE action plan and observe lessons at least once annually. Monitor termly tracking of pupil skills Ensure reporting requirements of school premium & deadlines are met. Purchase of new wall mounted gym equipment and playground markings Purchase real PE scheme for more focus on skills-based PE curriculum | As before Monitor impact of WSP on staff confidence & CPD needs identified Evaluate system for monitoring PE & lunchtime equipment stores for availability, access to & condition of equipment Whole school PE curriculum is skill based along Real PE ideas | As before Continue to monitor impact of WSP on staff confidence & CPD needs identified Continued monitoring of system for monitoring PE & lunchtime equipment stores for availability, access to & condition of equipment Evaluate impact of PE Curriculum based on real PE | All teachers delivering consistently high quality lessons 100% increase in teacher confidence to deliver key curriculum sports System in place to facilitate timely sharing of training and good practice All pupils make good progress. At least 90% secure in ARE. At least 30% exceeding All equipment appropriate, accessible and well maintained Teachers confident that curriculum equipment needs are met |

| Priority 2: to continue to improve activity levels and participation in physical activity of all children especially those less active children. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Monitoring | RAG Evaluation and Milestones July 2020 July 2021 July 2022 |  |  | Success Criteria |
| Improve tracking of children’s participation in PA both in & out of school Improved uptake of PA clubs including Change4life Improve signposting of children to community clubs Ensure at least 30 minutes of physical activity daily in curriculum time for all children | SL HT | SL HT | Using pupil voice through School Council develop PE passport to encourage participation in PA. Y4 Develop annual questionnaire to identify participation in PA both in & out of school & preferences /satisfaction with PE & PA clubs Advertise local community clubs to school population (notice board/ email/fliers/school website) At least one community club to pay a promotional visit. Contact less familiar clubs e.g fencing, archery Monitor staff knowledge of community clubs in the curriculum sports taught Improve termly tracking of pupils’ participation in PA clubs in & out of school hours Develop a more structured Change4Life programme using Change4life materials. Encourage family engagement of less active children with sharing/recognition of activity out of school e.g leaf from a family walk Contact local clubs for promotional materials e.g vouchers,taster sessions as incentives for children especially less active to join community clubs Improve structure of KS1 10 minute PE burst with short focused activities & KS2 daily mile through pedometers and counting steps. | As before Evaluate success of school passport & improve Monitor information acquired through pupil PE questionnaire & improve questionnaire Aim for further community clubs to pay promotional visits | Additional training needs identified Consider best way to monitor | Children demonstrate increased confidence and skills and demonstrate good progress from their starting point. All pupils participate in at least one physical activity club either inside or outside school |

| Priority 3: To continue to raise the profile of PE and PA within the school and extend external recognition for high quality PE and physical activity |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Monitoring | RAG Evaluation and Milestones July 2020 July 2021 July 2022 |  |  | Success Criteria |
| Continue to raise PE and PA profile through the school Identify and work towards achievement of Sainsbury’s School Games gold kite | Head teacher Subject Leader | Subject Leader Annual PE Audit Sainsbury’s School Games Mark criteria | Ensure intra and interschool competition covers sports with a range of governing bodies Develop & introduce PE passport Invite governors to intra and inter competition events. Report on PE events (twitter, Instagram, newsletter) | Evaluate and continue to develop PE passport | Evaluate impact of PE passport | Achieve Sainsbury’s School Games Gold kite |